## Reference Stories
Referential Story Number | Pool | Story Source | Story Summary (25 - 50 words)
1 | 1 | EECS 330 Lab 1 | Downloaded and installed Python 3.11, Conda, and Github Desktop. Created a private repository solely for EECS 330 Labs and invited the TA.
2 | 1 | EECS 649 Assignment 1 | Performed Logistical and Polynomial Regression on a data set through Colab which walked us through each step of the process.
3 | 1 | EECS 658 Assignment 1 | Combined code provided in previous lectures in order to evaludate the iris dataset on 7 different Machine Learning models.
4 | 2 | EECS 700 Assignment 2 | Analyzed and compared two biometric identification systems using provided similarity matrices. Generated normalized genuine and impostor score histograms, calculated decidability index (d′), plotted CMC curves, and identified performance ranks. Determined System2 as superior based on accuracy and robustness, and discussed expected performance decline in Rank-1 rate with larger subject enrollment.
5 | 2 | EECS 510 Project | Developed SoccermatchLang, a formal language to model and represent soccer match events. Defined syntax and grammar rules to capture gameplay sequences such as passes, goals, and substitutions. Implemented parsing and validation mechanisms to ensure event sequences adhere to real-world soccer constraints.
6 | 2 | EECS 330 Lab 3 | Implemented a Linked List using bare-bones starter code, which takes in an integer item and integer position, and inserts item at the given position. Additionally, implemented a reverse function that reverses the linked list and a replicate function.
7 | 3 | EECS 330 Lab 4 | Created a Deque using a Doubly-Linked-List. Implemented functions such as empty, get_size, push, push_front, pop, pop_front, front, back, resize, is_palindrome, and reverse_deque. Additionally, formulated test cases to ensure correctness and robustness of the Deque class.
8 | 3 | EECS 330 Lab 7 | Created a HashMap data structure with fully implemented functions of put, get, remove, and display. Utilized the created HashMap to implement a FlightNode class, which stores a list of commercial airline flights and their corresponding set of trips. Additionally, each flight stored a flight number, trip id, and number of passengers on the trip.
9 | 3 | EECS 388 Final Project | Designed an automatic braking system using a TFmini LiDAR sensor for object detection and distance measurement.ntegrated a deep neural network (DNN) model to predict and transmit steering angles to a HiFive board via UART. Programmed the embedded system in C and Python, demonstrating proficiency in serial communication and sensor integration.
10 | 5 | EECS 581 Project 2 | Completed maintenance of an existing minesweeper game from another EECS 581 team. Fixed functionality bugs, added new features, improved documentation.
11 | 5 | EECS 348 | Created a command line calculator that supported arithmetic and boolean operations. Followed a very specific syntax required by the user stories.
12 | 5 | EECS 665 Project 1 | Created a scanner using Flex for the in-progress compiler which outputs the token stream per spec and outputs errors to stderr. Implemented support of IDs, ints, strings, bool, void, and language-specific symbols while tracking its line and column. Handles illegal characters, unterminated/bad strings, and 32-bit overflow.
13 | 8 | EECS 581 Project 1 | Planned, designed, and created a fully functional minesweeper game with our team in EECS 581. Backend with all the minesweeper functionality, and a GUI with sufficient detail.
14 | 8 | EECS 665 Project 2 | Built a Bison-based parser into the in-progress compiler. Created node types for each symbol, declaration, and type in the language. Implemented full language grammar utilizing Bison and Flex with explicit precedences and associativities.
15 | 8 | EECS 348 Final Project | Developed a Boolean expression evaluator capable of simulating logic circuits with operations such AND, OR, NOT, NAND, and XOR. Inmplmemnted unit tests to validate expression evaluations and ensure software reliability.
16 | 13 | EECS 665 Project 4 | Implemented a name analysis checker into a compiler, which parses and tokenizes the input, collects each semantic symbol (e.g. variable or function) of the input and builds a correspondance between the identifier and symbol in a symbol table.
17 | 13 | EECS 447 Project | Developed an end-to-end relational database system to handle media inventory, client memberships, borrowing, returns, reservations, and fines. Conducted domain modeling and requirements engineering to identify key entities and relationships. Produced ER diagrams and normalized schema to 3NF/BCNF.
18 | 13 | EECS 665 Project 5 | Implemented an AST type checker into the in-progress compiler. Assigned expression types, reported spec-complaint errors to stderr, enforced operator/operand rules, calls, arrays, and conditions. Ensured errors were not excessive.

## Requirement Stack
Requirement ID | Description | Story Points | Priority | Sprint No.
1.1 | Define system architecture | 3 | 1 | 1 | Project Summary: We want to create an LLM assisted weather web app that not only displays key weather information, but provides a natural language summary of the weather, and allows for limited conversation in regard to the weather.
1.2 | Create repository and initial file structure | 2 | 2 | 1
1.3 | Configure enviornment: set up enviornment varaibles for API keys | 2 | 3 | 1
1.4 | Create and complete the README file in github. (dependecies, setup steps, run instructions, etc.) | 2 | 4 | 1
1.5 | Create simple skeleton website (github hosting, static, focus on design over functionality) | 5 | 5 | 1
1.6 | Evaluate and select weather data source (data API) to be integrated. | 2 | 6 | 1
1.7 | Setup weather database API to retrieve realtime weather information (temp, precipitation, cloud cover, UV, wind, storm, maybe AQI, etc). Static location, console output. | 5 | 7 | 1 | Total Story Points for Sprint 1: | 21
2.1 | Format response, extract and structure weather fields | 3 | 8 | 2
2.2 | Implement error handling for API | 3 | 9 | 2
2.3 | Test cases/ verify correctness of API responses | 2 | 10 | 2
2.4 | Choose LLM API and configure LLM provider | 2 | 11 | 2
2.5 | Design prompt structure for weather summary | 2 | 12 | 2
2.6 | Setup of Google Gemini API pipeline. | 1 | 13 | 2
2.7 | Implement summary within Gemini, return generated text | 5 | 14 | 2
2.8 | Test cases/ verify summary quality | 2 | 15 | 2 | Total Story Points for Sprint 2: | 20
3.1 | Integrate Chat UI with Gemini (Connect Gemini to chatbox) | 3 | 16 | 3
3.2 | Display key weather information on website (Connect UI to weather API), display temperature, icons, etc. | 3 | 17 | 3
3.3 | Implement location search, allow user to query by city or GPS | 3 | 18 | 3
3.4 | Add unit switching (Celsius to Fahrenheit) | 2 | 19 | 3
3.5 | Create loading and error states within UI | 2 | 20 | 3
3.6 | Test cases/ verify correctness of location weather, and unit conversion | 2 | 21 | 3
3.7 | Design chat UI component and integrate with existing layout | 5 | 22 | 3 | Total Story Points for Sprint 3: | 20
4.1 | Create and implement backend chat handler (Chat UI and Gemini) | 5 | 23 | 4
4.2 | Add conversational limits and constraints, restrict to weather-related topics | 2 | 24 | 4
4.3 | Implement error handling for chat. | 3 | 25 | 4
4.4 | Test cases/ Chat conversational flow, topics, verify correctness | 2 | 26 | 4
4.5 | UI Polish (Make sure website is consistent and professional) | 2 | 27 | 4
4.6 | Final responsiveness and polish (loading results, finalize for deployment) | 3 | 28 | 4
4.7 | Update README and documentation | 2 | 29 | 4
4.8 | Create demo video and retrospective | 3 | 30 | 4 | Total Story Points for Sprint 4: | 22
| Display Gemini interaction on the website. (prompt the summary) | 2
| Create AI Chat Box UI (Integrate with existing layout) | 2
| Integrate Chat UI with Gemini (Connect Gemini to chatbox) | 3
| Integrate Summary UI with Gemini (Connect Gemini to summary) | 2
| Create AI Chat Box UI (Integrate with existing layout) | 2